## Release
Release | SubRelease | PR | Branch Creation | Merge to Master | Pipeline | Test Deployment # | Test Deployment Time | Prod Deployment # | Prod Deployment Time | Migration Files | Fixture Dataload Files | Merged to Develop | Comments
V0.1.0 | N/A | N/A | 2018-04-17 15:00 | N/A | client-47 tfrs-85 | client-48 tfrs-85 | 2018-04-17 15:30 | client-46 tfrs-72 | 2018-04-18 15:30 | N/A | core fixtures and ftrs internal users | N/A | was the first release deployed, but the resouces limits are adjusted after that.
| V0.1.0.1 | #236 | N/A | 2018-04-25 09:50 | client-39 tfrs-47 | client-49 tfrs-86 | 2018-04-25 10:15 | N/A | N/A | N | N | N
| V0.1.0.2 | #240 | N/A | 2018-04-26 09:15 | client-40 tfrs-48 | client-50 tfrs-87 | 2018-04-26 09:20 | N/A | N/A | 0005_auto_20180424_1445.py 0006_auto_20180424_1527.py 0007_credittradehistory_compliance_period.py | compliance_periods.json | N
| V0.1.0.3 | #245 | N/A | 2018-04-26 16:00 | client-41 tfrs-49 | client-51 tfrs-88 | 2018-04-26 16:30 | client-47 tfrs-73 | 2018-05-01 10:00 | N | N | N
| V0.1.0.4 | #262 | N/A | 2018-05-01 15:15 | tfrs-50 | tfrs-89 | 2018-05-01 15:25 | tfrs-74 | 2018-05-01 15:35 | N | organization_vancouver_island_propane_services.json test_tfrs_users_MichaelRensing.json | 2018-05-03 #267
| V0.1.0.5 | #278 | N/A | 2018-05-08 16:00 | tfrs-52 | tfrs-91 | 2018-05-08 16:30 | tfrs-75 | 2018-05-10 11:00 | N | N | 2018-05-16 #292 | No migrations to apply. Your models have changes that are not yet reflected in a migration, and so won't be applied. Run 'manage.py makemigrations' to make new migrations, and then re-run 'manage.py migrate' to apply them.
| DB Update 2018-05-11 | N/A | N/A | N/A | N/A | N/A | 2018-05-11 | N/A | 2018-05-11 | N/A | N/A | N/A | the scripts are used to fix trello #592 Correction ¦ Fix errors made while entering historical data ¦ https://github.com/bcgov/tfrs-docs/blob/master/docs/system/data_adjustments.md "Changing the Respondent from a Credit Trade from one organization to another"
| DevOps Updates | #291 | N/A | 2018-05-16 #291 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2018-05-16 #292 | update backend/Jenkinsfile and frontend/Jenkinsfile to use podTemplate
| DB Update 2018-05-24 | N/A | N/A | N/A | N/A | N/A | 2018-05-24 | N/A | 2018-05-24 | N/A | N/A | N/A | the script is used to update the user id i8 authentication_id https://github.com/bcgov/tfrs-docs/blob/master/docs/system/data_adjustments.md "Fixing a duplicate authorization_id"
V0.2.0 branch created May 23, 2018
There is a incorrect deployment for v0.2.0.1on client on prod, deployment #50 is actually caused by #49 is rollbaced to #47 which is v0.1.0, so #50 is same as #47
V0.2.0 | N/A | #306 | 2018-05-24 | 2018-05-24 #PR306 | tfrs-54 client-44 | tfrs-107 client-55 | 2018-05-25 | N/A | N/A | 0008_auto_20180507_1734 0009_signingauthorityassertion_signingauthorityconfirmation | N/A | N/A
| v0.2.0.1 | #315 | N/A | 2018-05-29 | tfrs-55 client-45 | tfrs-108 client-57 | 2018-05-29 12:00pm | N/A | N/A | N/A | N/A | N/A
| V0.2.0.2 | #319 | N/A | 2018-05-29 | tfrs-56 client-46 | tfrs-109 client-58 | 2018-05-29 14:00pm | N/A | N/A | 0010_auto_20180529_2003.py | N/A | N/A
| v0.2.0.3 | (#312, #317)

## Fixtures
core fixtures | tfrs internal users | test data | test users
credit_trade_statuses | test_tfrs_users | test_credit_trades | test_users
credit_trade_types | test_tfrs_users_MichaelRensing | test_organization_balances
organization_actions_types
organization_government
organization_statuses
organization_types
organization_fuel_suppliers
organization_balance_gov
credittradezeroreason

## Platform and Library Upgrades
| Date/Time on Dev | Date/Time on Test | Date/Time on Prod | Impacted release on Prod | Notes
Frontend Nodejs Upgrades
Backend PythonDjango upgrades
Postgresql Upgrades
Plateform Upgrades | Apr 24 2018 |  |  | V0.1.0 | CNS Upgrade, New volume provisioning will be disabled during the change but existing volumes aren't expected to have issues.

## ProdDBBackup
| SQLDump | Base Backup | PIT Backup
20180423 | frs-20180423-1345.gz | tfrs-prod-20180423-1550.tar | 000000010000000000000004.00000028.backup
20180510 | tfrs-20180510-1331.gz | N/A | N/A
20180511 | tfrs-20180511-1328.gz | N/A | N/A

## ISSUESPrs
Release | Issues | Trello | Pull Request | Deployed on Dev | Deployed on Test | Deployed on Prod | Deployment # | comments
V0.1.0.1 | 230 | 574 | 232 | N/A | Yes | No | client-39 tfrs-46
| 231 | 575
V0.1.0.2 | 233 | 578 | 234 | N/A | will do
| 231 | 575 | 235 | N/A
| N/A | N/A | 229 | N/A
V0.2.0 | 237 | 579 | 239 |  | N/A | N/A
| 238 | 581
| N/A | N/A | 229 |  |  |  |  | move openshift folder